## TestScenarios
Project Name | Startech.bd.com
Reference Document | FRS
Created By | Md.Tashfiquzzaman
Creation Date | 20-08-2023
Approval Date | 22-08-2023
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the URL in different browsers. | P0 | 1
TS_002 |  | Validate the "Register Account" functionality | P1 | 30
TS_004 |  | Validate the working of the "Login" functionality. | P0 | 35
TS_006 |  | Validate the working of "Add to cart" functionality. | P1 | 5
TS_006 |  | Validate the working of " Total amount" functionality. | P1 | 1
TS_009 |  | Validate the working of "Screenshot" functionality. | P4 | 1
TS_010 |  | Validate the working of "Search Bar" functionality. | P4 | 1
TS_012 |  | Validate the working of "Gadget Fest" functionality. | P5 | 1
TS_013 |  | Validate the working of "Get offer" functionality. | P5 | 5
TS_014 |  | Validate the working of "OTP" functionality. | P1 | 5
TS_015 |  | Validate the working of "Forgotten Password?" functionality. | P2 | 10
TS_016 |  | Validate the working of "Mobile Deal" functionality. | P3 | 1
TS_017 |  | Validate the working of "PC Builder" functionality. | P3 | 1
TS_018 |  | Validate the working of "accessories"functionality. | P4 | 1
TS_019 |  | Validate the working of "office-equipment" functionality. | P5 | 1
TS_020 |  | Validate the working of "SUPPORT"functionality. | P5 | 1

## TestCase
Product Name |  | yellow.net | TC Start Date | 2024-08-01 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Account | TC End Date | 17/08/2023 | TC Execution End Date | - - |  |  |  |  | PASS | 106
Epic |  |  | Test Case Developed By | Fariea Tabassum Mow | Browser (tested) | Yes |  |  |  |  | FAIL | 24
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | Yes |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 130
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge | 1. Go to different browsers. 2. Search 'Yellow' 3. Go to the website. |  |  | Passed
2 | User Management | Ui Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1.Go To the Url 2. Click 'Create an Account' button in right corner. 3. Check the spelling and grammer of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1.Go To the Url 2. Click 'Create an Account' button in right corner. 3. Check the font, text, color and style |  |  | Passed
4 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Found as per expectation | N/A | 1.Go To the Url 2. Click 'Create an Account' button in right corner. 3. Check mandatory field marked with red asterisk |  |  | Passed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1.Go To the Url 2. Hover over every field |  |  | Passed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1.Go To the Url 2. Click 'Create an Account' button in right corner. 3. Check the alignment of the field |  |  | Passed
7 |  |  |  | Checking 'Remember Me' option in the Registration form | Should be present | Not found as per expectation | N/A | 1.Go To the Url 2. Click 'Create an Account' button in right corner. 3. Go to the register field 4. Check 'Remember me' option. | remember me option.png |  | Failed
8 |  |  |  | Checking 'Eye Icon' in the password field | Should be present | Not found as per expectation | N/A | 1.Go To the Url 2. Click 'Create an Account' button in right corner. 3. Go to the register field 4. Check 'Eye Icon' in the password field. | eye icon.png |  | Failed
9 |  |  |  | Checking 'Password confirmation' field present or not in the registration field | Should be present | Not found as per expectation | N/A | 1.Go To the Url 2. Click 'Create an Account' button in right corner. 3. Go to the register field 4. Check 'Password confirmation' in the password field. | password confirmation.png |  | Failed
10
11 | User Management | Functional Testing | Sign Up | Verify by clicking on the ‘CREATE an ACCOUNT’ button for blank input. | User can't be able to register | Found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.keep mandatory field blank |  |  | Passed
12 |  |  |  | Checking that First name and Last name field is case insensitive | Should be case sensitive | Not found as per expectation | Fariea tAbASSumu mOW | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Input Fariea tAbASSumu and mOW for First Name and Last Name field |  |  | Failed
13 |  |  |  | Entering blank at first position in First Name and Last Name field | Shouldn't be accepted this input | Accept this input | Fariea tAbASSumu mOW | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Input with spaces Fariea tAbASSumu and mOW for First Name and Last Name field | paces in first and last name.png |  | Failed
14 |  |  |  | Giving special character in First Name and Last Name field. | Shouldn't be accepted this input | Accept this input | #66778*()>>,, **777&&&<<;; | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Input special Character #66778*()>>,, and **777&&&<<;; for First Name and Last Name field | special character.png |  | Failed
15 |  |  |  | Inputing First Name and Last Name with numbers | Shouldn't be accepted this input | Accept this input | 01772977889 38887477829 | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Input numbers 01772977889 and 38887477829 for First Name and Last Name field | taking numbers.png |  | Failed
16 |  |  |  | Giving invalid email format. | Shouldn't be accepted this input | Found as per expectation with an error message | farieamow.gmailcom | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Input invalid email farieamow.gmailcom in email field |  |  | Passed
17 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | farieamow304@gmail.com | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Fill the email address with already registered email |  |  | Passed
18 |  |  |  | Checking by inputing valid email format | Should accept the valid email input | Found as per expectation | farieamow304@gmail.com | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Fill the valid email address |  |  | Passed
19 |  |  |  | Giving space in first position of Email field | Shouldn't be accepted this input | Found as per expectation | farieamow304@gmail.com | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Fill the valid email address with spaces in first position |  |  | Passed
20 |  |  |  | Checking password values are masked | Should be masked | Found as per expectation | 12345 | 1.Go to the url https://www.yellowclothing.net/ 2. Check password field |  |  | Passed
21 |  |  |  | Checking that password should be strong with combination of upper case,lower case alphabets, digits and special character. | Strong password should be accepted | Not found as per expectation | 12345 | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Inter password |  |  | Failed
22 |  |  |  | Checking password confirmation field | Password confirmation field should be presented | Not found as per expectation |  | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Check password confirmation field | password confirmation.png |  | Failed
23 |  |  |  | Checking registration button with valid credentials | Should allow user to register | Found as per expectation | First Name: Fariea Last Name: Mow Email: Farieamow304@gmail.com Password: 12345 | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Click on the Create an account button |  |  | Passed
24 |  |  |  | Checking confirmation mail sent to the registered email | Sent successfully | Found as per expectation | First Name: Fariea Last Name: Mow Email: Farieamow304@gmail.com Password: 12345 | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Click on the Create an account button |  |  | Passed
25
26 | User Management | Usability | Sign Up | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfull |  | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Click on the Create an account button |  |  | Passed
27 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Enter tab in every field |  |  | Passed
28 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Enter enter in the every field |  |  | Passed
29
30 | User Management | Ui Testing | Log in | Verify all fields related to Log In present on the Log In form | Should be present. | Found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. |  |  | Passed
31 |  |  |  | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Check spelling or Grammar of sign in page. |  |  | Passed
32 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Check font, text and color. |  |  | Passed
33 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Check Red asterisk. |  |  | Passed
34 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Check alignment of the page |  |  | Passed
|  |  |  | Checking 'Remember Me' option in the Sign In form | Should be present | Not found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Check remember Me option | remember me log in.png |  | Failed
|  |  |  | Verify that forget password link should be present on the login screen. | Should be present | Found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Check remember Me option |  |  | Passed
35 |  |  |  | Checking 'Eye Icon' in the password field | Should be present | Not found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Check Eye icon in password field | log in eye icon.png |  | Failed
36
37 | User Management | Functional | Log In | Verify by clicking on the ‘Log in' button for blank input. | User can't be able to log in | Found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Keep mandatory field blank |  |  | Passed
38 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | 12345 | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Input values in password field and check if it is masked |  |  | Passed
39 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | fariea@gmail.com 2345 | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Input wrong values in email and password field |  |  | Passed
40 |  |  |  | Checking login valid credentials in email and password field | Should allow user to register | Found as per expectation | Email: farieamow304@gmail.com Password: 12345 | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Input values in email and password field |  |  | Passed
41 |  |  |  | Verifying ‘Forgot Password’ functionality | Should sent an email for recovering password | Found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Click on the Forget Password 4.Check resent email. |  |  | Passed
42 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3.Click on 'Forgot Password' 4. Check the registered email |  |  | Passed
43 |  |  |  | Verifying the functionality of 'Set a New Password' | Should provide a new input for setting new password | Found as per expectation | N/A | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3.Click on 'Forgot Password' 4. Check the registered email 5.5. Click on 'Set up a New Password' |  |  | Passed
44 |  |  |  | Verifying login with the newly changed password | Should allow user to login | Found as per expectation | Email: farieamow304@gmail.com Password: 123456 | 1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3.Click on 'Forgot Password' 4. Check the registered email 5. Enter new password 6. Click on login |  |  | Passed
69 | Header | ui testing | Header | Verify the header section added on the website | Should be added | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the header section. |  |  | Passed
70 |  |  |  | Verify header section is aligned | Should be aligned | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the alignment of the header section. |  |  | Passed
71 |  |  |  | Verify icons aligned with the text. | Icons should be aligned with the text . | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the alignment of the icon with text of header section. |  |  | Passed
|  |  |  | Verify whether link text should be readable or not. | Should be readable | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the text of links. 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and |  |  | Passed
|  |  |  | Verify the logo of the website added or not on the header. | Logo of the website should be added | Not found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the logo of the website. 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and |  |  | Failed
|  |  |  | Verify the same header used on the whole website pages. | Should be used the same header | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the same header section on the whole website |  |  | Passed
|  |  |  | Verify header is sticky on the whole page or fixed as per requirements | Should be sticky or fixed | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the position of header section on the whole website 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and |  |  | Passed
|  |  |  | Verify on the mouse hover color change or not for the link added on the header menu. | Should be changed | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the hover over of header section on the whole website |  |  | Failed
|  |  |  | Verify that selected header links should remain ACTIVE to inform the user about the clicked screen/page. | Should be active | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the links active to inform user of header section on the whole website |  |  | Passed
|  |  |  | Verify search bar is added to the header menu or not. | Should be added | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the search ba on header section on the whole website |  |  | Passed
|  |  |  | Verify header and body section should not look the same. | Should be different | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check header and body section of website |  |  | Passed
|  |  |  | Verify dropdown options added on header shown on mouse hover | Should be shown | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the dropdown option of the website |  |  | Passed
72 |  |  |  | Verify icons added should be related to the link text. | Icons added should be related to the link text. | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the icons related to the link text |  |  | Passed
73
| Header | Functional Testing | Search bar | Enter a valid product name and ensure relevant results are displayed. | Should be displayed | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the search bar with product name. |  |  | Passed
|  |  |  | Check if search results show product images, names, prices, and descriptions. | Should be shown | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the search bar with product name. |  |  | Passed
|  |  |  | Verify that filters (ex: sorting, category, price range) work correctly with search results. | Filters should work correctly | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the search bar with product name. |  |  | Passed
|  |  |  | Enter an empty search query and ensure it doesn't initiate a search. | Shouldn't initiate a search | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the search bar with empty search. |  |  | Passed
|  |  |  | Enter a invalid product name and ensure that give a 'No result found' message | Should give a message | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the search bar with invalid product search. |  |  | Passed
|  |  | Shopping Cart | Verify that the 'shopping Cart' link navigate properly or not | Should be navigated | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the shopping cart option |  |  | Passed
|  |  | Wish List | Verify that the 'wish list' link navigate properly or not | Should be navigated | Not found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the wish list option |  |  | Failed
|  |  | Sign In | Verify that the 'Sign In' link navigate properly or not | Should be navigated | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check theSign in option |  |  | Passed
|  |  | Create an Account | Verify that the 'Create an Account' link navigate properly or not | Should be navigated | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the Create an account option |  |  | Passed
|  |  | Yellow Logo | Verify that the 'yellow' link navigate properly or not | Should be navigated | Found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the logo option |  |  | Passed
| Footer | Ui testing | Footer | Verify the footer section is aligned at the end of the page. | Should be aligned | Found as expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the alignment of footer |  |  | Passed
|  |  |  | Verify there should be no extra white space at the end of the footer on high screen resolutions. | Shouldn't be no extra white space | Found as expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check the extra spaces of footer |  |  | Passed
|  |  |  | Verify element is aligned at the footer section or not. | Should be aligned | Found as expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check alignment footer |  |  | Passed
|  |  |  | Verify footer section should be the same for all pages. | Should be same for whole website | Found as expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check footer section is same for whole website |  |  | Passed
|  |  |  | Verify the logo shown at the footer. | Should be shown | Not found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check footer section logo |  | logo missing.png | Failed
|  |  |  | Verify all social links with icons added on the footer. | All social links should be added | Found as expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check footer section social icons |  |  | Passed
|  |  |  | Verify no spelling mistakes for the text on the footer section. | Shouldn't be done any spelling mistke | Found as expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check spelling of footer section |  |  | Passed
|  |  |  | Verify no broken link is found on the footer. | No broken link shouldn't be found | Found as expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check broken link of footer section |  |  | Passed
|  |  |  | Verify whether the subscribe to the newsletter email field with subscribe button present or not. | Should be present | Found as expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check email fiels with subscription button of footer section |  |  | Passed
|  |  |  | Verify mouse cursor changes from a pointer to a hand on the link. | Should change | Found as expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check mouse cursor changes to the link of footer section |  |  | Passed
|  |  |  | Verify whether the copyright section is added to the footer or not. | Should be added | Found as expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check copyright icon of footer section |  |  | Passed
|  |  |  | Verify correct year was added to the footer section or not. | Correct year should be added properly | Not found as per expectation |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check correct year icon of footer section |  | Not showing correct year.png | Failed
| Footer | Functional Testing | Footer | Verify by clicking on the links correct pages should be loaded. | Correct page should be loaded | Correct page loaded |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check footer page links work or not |  |  | Passed
|  |  |  | Verify validation on the email field for subscribing to the newsletter added or not | Validation Should be added | Validation added in email fiels |  | 1. Go to the URL https://www.yellowclothing.net/ 2.Check validation on the email field for subscribing to the newsletter of footer page |  |  | Passed
|  |  |  | Verify an error message shown on blank input on click on the Subscribe button. | Error meaage should be given | Error message given | N/A | 1. Go to the URL https://www.yellowclothing.net/ 2.Check an error message shown on blank input on click on the Subscribe button of footer page |  |  | Passed
|  |  |  | Verify confirmation message should be shown if the user subscribed successfully | Confirmation message should be shown | Found as per expectation | N/A | 1. Go to the URL https://www.yellowclothing.net/ 2.Check confirmation message shown when the user subscribed successfully of footer page |  |  | Passed
| Home Page | Ui Testing | Video Components | Ensure the video player UI elements (buttons, progress bar, controls) maintain a consistent appearance across different browsers and devices | Should maintain a consistent appearance different browser | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video ui elements |  |  | Passed
|  |  |  | Varify the video quality well or not | Should be well qualityfull | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video quality |  |  | Passed
|  |  |  | Verify that the video adapts well to different screen sizes (desktop, tablet, mobile) using responsive design principles | Should be adapts well | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video in different browser |  |  | Passed
|  |  |  | Ensure the video load quality is well or not | Load quality should be well | Not found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video load quality | poor video loading.png |  | Failed
|  |  | Slider | Verify that the slider accurately displayed | Should be accurately displayed | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider |  |  | Passed
|  |  |  | Verify that the slider maintains a consistent appearance across different browsers and devices. | Should maintain a consistent appearance | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider |  |  | Passed
|  |  |  | Confirm that the slider adapts well to different screen sizes and orientations. | Should adapts well to different screen sizes and orientations. | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider |  |  | Passed
|  |  |  | Ensure slider width and height. | Should have right width and height | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider width and height |  |  | Passed
|  |  |  | Ensure corresponding image should not get crop. | Image Should not get crop | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider image |  |  | Passed
|  |  | Photo Cards | Verify that there are no additional buttons or controls displayed during video playback. | Additional Button should not added to control the video | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Photo card |  |  | Passed
|  |  |  | Confirm that the video is muted, and no sound is played during the playback. | The video should be muted | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Photo card sound |  |  | Passed
|  |  |  | Test the feature on different browsers to ensure consistent behavior. | The video feature should be consistent in different broser | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Photo card |  |  | Passed
|  |  |  | Check responsiveness on various devices, including desktops, tablets, and mobile phones. | Should responsive in different browser | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Photo card |  |  | Passed
|  |  |  | Confirm that the video starts playing when the cursor is placed on the photo card. | The video should playing | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Photo card |  |  | Passed
|  |  |  | Ensure the video stops playing when the cursor is moved away from the photo card. | The video should stop | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Photo card |  |  | Passed
|  |  | Quick Add button | Verify button present on the page as per the design on the web page. | The button should be as per as design | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Quick Add button design |  |  | Passed
|  |  |  | Verify the button colour same as per design. | The button color should be as per as design | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Quick Add button color design |  |  | Passed
|  |  |  | Verify width and height for the button. | The button should be right width and height | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Quick Add button width and height design |  |  | Passed
|  |  |  | Check button text is readable or not by verifying button text size. | Button text should be readable | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Quick Add button readable |  |  | Passed
|  |  |  | Verify button text colour should be visible on the button. | Button text should be visible | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Quick Add button text is visible |  |  | Passed
| Home Page | Functional Testing | Video Components | Verify that the video plays correctly when initiated. | Video should be played correctly | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video. |  |  | Passed
|  |  |  | Test the basic controls such as play, pause, stop, and rewind. | The basic controls shold perform well | Not found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video basic controls |  |  | Failed
|  |  |  | Check that the video can be played in different resolutions and quality settings | Should be played | Not found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video |  |  | Failed
|  |  |  | Confirm that the video can be played in fullscreen mode. | Should be played | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video in full screen |  |  | Passed
|  |  |  | Test entering and exiting fullscreen mode and ensure the video scales appropriately. | Should scale properly | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video |  |  | Passed
|  |  |  | Test the volume control functionality, including muting and unmuting. | Should be volume controls well | Not found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video volume |  |  | Failed
|  |  |  | Verify that the volume settings are applied consistently. | Should be consistent | Not found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video |  |  | Failed
|  |  |  | Test the behavior during buffering and loading. | Should not buffering | Not found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video |  |  | Failed
|  |  |  | Confirm that the video loads efficiently without interruptions or excessive buffering time. | Video loads without buffering | Not found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video |  |  | Failed
|  |  |  | Ensure appropriate error messages are displayed to the user when the video isn't playing. | Should give error message | Not found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video |  |  | Failed
|  |  |  | Verify that the video plays correctly on different devices, including desktops, laptops, tablets, and mobile phones. | Should be played correctly | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage video |  |  | Passed
|  |  | Slider | Test the ability to navigate between images using the slider controls. | Should be navigated | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider |  |  | Passed
|  |  |  | Verify that images change smoothly and without glitches. | Should be changed smoothly | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider |  |  | Passed
|  |  |  | Test the functionality of navigation controls | Should control well | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider |  |  | Passed
|  |  |  | Verify the image slider supports captions or descriptions, test their visibility and accuracy. | Should be visible | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider |  |  | Passed
|  |  |  | Confirm that users can move forward and backward through the images. | Can be moved | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider |  |  | Passed
|  |  |  | Test the loading of images, especially in scenarios with slow internet connections. | Should be loaded | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider |  |  | Passed
|  |  |  | Verify that images preload efficiently to prevent delays during transitions. | Should be preload well | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider |  |  | Passed
|  |  | Photo Card | Verify that playing a video in photo card. | Should be played | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Photo card |  |  | Passed
|  |  |  | Verify that the photo card is clickable or not | Should be clickable | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Photo card |  |  | Passed
|  |  |  | Verify that when click on the photo card it takes to the right page | Should go to the right page | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Photo card |  |  | Passed
|  |  |  | Check the loading time of the video | Should play instantly | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Photo card |  |  | Passed
|  |  | Quick Add button | Click on the "Quick Add" button and verify that it triggers the expected action. | Should triggers the expected action | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage slider |  |  | Passed
|  |  |  | Confirm that clicking the "Quick Add" button opens the corresponding form or modal for adding information. | Should be opened | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Quick Add button |  |  | Passed
|  |  |  | Verify button text related to the functionality of the tool on the web page. | Should be relateable | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Quick Add button |  |  | Passed
|  |  |  | Verify button is enabled/clickable or not by clicking on the button. | Should be clickable | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Quick Add button |  |  | Passed
|  |  |  | Verify user can be able to open button link in a new tab by right click on the button | Should be opened | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Quick Add button |  |  | Passed
|  |  |  | Verify whether pressing the Ctrl button on the keyboard and click on the button opens a new tab or not. It should be according to the requirements. | Should be opened | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Quick Add button |  |  | Passed
|  |  |  | Verify the whole button should be clickable not only the button text. | Should be clickable the whole button | Found as per expectation | N/A | 1. Go to the url https://www.yellowclothing.net/ 2.Check homepage Quick Add button |  |  | Passed
Verify the desired action performed on click on the button or not.
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Yellow Fashion Company
Module Name | Account. |  |  |  |  | Total No. | Status
Feature Name | Register Account, Account Login Homepage. Header & Footer
Test Case Version | 1 |  |  |  |  | 106 | PASS
Written By | Fariea Tabassum Mow |  |  |  |  | 24 | FAIL
Executed By | Fariea Tabassum Mow |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 106 | 24 | 0 | 0 | 130
Grand Total | 106 | 24 | 0 | 0 | 130
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
# SL 01
Issue: Taking special character in First Name and Last Name field.
Reproducing Steps:
1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Input special Character #66778*()>>,, and **777&&&<<;;
Env: Production.
Module: Create an Account(Register)
Priority:Medium
Severity:Minor
special character.png
Expected: Should not taking special character in First name and last name field
Responsible QA: Fariea Tabassum Mow
Bug Reporting
# SL 02
Issue: Missing of password confirmation field
Reproducing Steps:
1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Check password confirmation field
Env: Production
Module: Register
Severity: P2
password confirmation.png
Responsible QA: Fariea Tabassum Mow
Bug Reporting
# SL 03
Issue: Missing 'Eye Icon' in the password field
Reproducing Steps:
1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Check Eye icon in password field
Env: Production.
Module: Log in
Severity: P4
Eye icon password.png
Responsible QA: Fariea Tabassum Mow
Bug Reporting
# SL 04
issue:First name and Last name field takes spaces in first position
Reproducing Steps:
1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Input Fariea tAbASSumu and mOW for First Name and Last Name field
Env: Production
Module: Register
Severity: P5
spaces in first and last name.png
Responsible QA: Fariea Tabassum Mow
Bug Reporting
# SL 05
issue: Website doesn't show the correct year
Reproducing Steps:
1. Go to the URL https://www.yellowclothing.net/ 2.Check correct year in footer section
Env: Production
Module: Login
Severity: P6
Not showing correct year.png
Responsible QA: Tashfiquzzaman

## Copy of Bug report
Bug Reporting
# SL 01
Issue: Taking special character in First Name and Last Name field.
Reproducing Steps:
1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Input special Character #66778*()>>,, and **777&&&<<;;
Env: Production.
Module: Create an Account(Register)
Priority: Medium
Severity: Minor
special character.png
Expected: Should not taking special character in First name and last name field
Responsible QA: Fariea Tabassum Mow
Bug Reporting
# SL 02
Issue: Missing of password confirmation field
Reproducing Steps:
1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Check password confirmation field
Env: Production
Module: Register
Severity: P2
password confirmation.png
Responsible QA: Fariea Tabassum Mow
Bug Reporting
# SL 03
Issue: Missing 'Eye Icon' in the password field
Reproducing Steps:
1.Go to the url https://www.yellowclothing.net/ 2.Go to the Sign In page. 3. Check Eye icon in password field
Env: Production.
Module: Log in
Severity: P4
Eye icon password.png
Responsible QA: Fariea Tabassum Mow
Bug Reporting
# SL 04
issue:First name and Last name field takes spaces in first position
Reproducing Steps:
1.Go to the url https://www.yellowclothing.net/ 2.Go to the Create an Account page 3.Input Fariea tAbASSumu and mOW for First Name and Last Name field
Env: Production
Module: Register
Severity: P5
spaces in first and last name.png
Responsible QA: Fariea Tabassum Mow
Bug Reporting
# SL 05
issue: Website doesn't show the correct year
Reproducing Steps:
1. Go to the URL https://www.yellowclothing.net/ 2.Check correct year in footer section
Env: Production
Module: Login
Severity: P6
Not showing correct year.png
Responsible QA: Tashfiquzzaman

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (130/130)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/130)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (106/130)*100 = 82%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (24/130)*100 = 18%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/130)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A